## Requirement
| Work to do | Assigned to | Control/QA | Docs | SCRIPT | TEMPLATES
LEAD MODULE New Leads -> Assign the leads Sales -> Assigned Leads -> Followp with Assigned Leads like proposal etc -> Potential Leads -> Quote Sent -> Waiting for Govt Approval -> Govt. Approved. Contacts and Deal Module Installation -> Payment -> Deal Won.
Steps - 1 | After the Lead Approval
1 | Check sale | Nick/Jas | Nav | Check list 1
2 | Make Quote(Sign the quote digitally using zoho sign) | Nick/Jas/Kiki | Nav
3 | Upload folder(Document Management) | Nick/Jas/Kiki | Nav
4 | Upload CRM | Nick/Jas/Kiki | Nav
5 | Welcome Call / Zoho update | Jas/Nick/Kiki | Nav |  | SCRIPT 1 | Template 1
6 | Draft solar vic quote | Nick/Jas/Kiki | Nav
7 | submitted solar vic quote/finalize sale(Govt Portal) | Nav
8 | Send Email to cust regarding quote | Nick/Jas | Nav |  |  | TEMPLATE 2
9 | Send link to cust regarding solar vic portal | Jas/Nick/Nav
10 | Process call(After submit the govt portal by the customer) | Jas/Nick/Nav |  |  | SCRIPT 2
11 | Follow up with cust regarding approval(Task to customer for approval) | Jas/Nick/Nav |  |  | SCRIPT 3
Steps - 2 | After the approval
1 | Check installer availability | Nav/Nick
2 | Plan installation | Nav/Nick
3 | Call customer and date confirmation | Nav/Nick |  |  | SCRIPT 4
4 | Upload info on bridge select | Sanju/Nick/Nav
5 | Send email to installer | Sanju/Nick/Nav |  |  |  | TEMPLATE 3
6 | Make the invoice | Sanju/Nick/Nav
7 | Place the order | Sanju/Nick/Nav
8 | Email pickup details to transport guy | Sanju/Nick/Nav |  |  |  | TEMPLATE 4
9 | Send invoice to cust | Sanju/Nick/Nav |  |  |  | TEMPLATE 5
10 | Call cust and collect the money | Sanju/Nick/Nav |  |  | SCRIPT 5
Steps - 3 | After the Installation
1 | On installation day - check bridge select photos, panel verify | Nick/Sanju/Nav
2 | Call cust for further process | Nick/Jas/Nav |  |  | SCRIPT 6
3 | Collect paperwork from installer | Nick/Sanju/Nav
4 | Check EWR, EG & CES | Nick/Sanju/Nav
5 | Check details on bridge select and upload CES | Nick/Sanju/Nav
6 | Upload STC on Rec Reg | Nick/Sanju/Nav
7 | Payment claim on solar vic | Nick/Sanju/Nav
8 | Upload the customer folder with all docs | Nick/Sanju/Nav
9 | Call cust for paperwork and wi fi setup | Nick/Jas/NAv |  |  | SCRIPT 7
10 | Raise the connection | Nick/Sanju/Nav |  |  |  | TEMPLATE 6
11 | Send paperwork to cust | Nick/Sanju/Nav |  |  |  | TEMPLATE 7
12 | Thank you / Review call to cust (After paper work done after 7 days) Make it process done stage. | Nick/Jas |  |  | SCRIPT 8
13 | Curtesy call after 3 months(After installation) | Nick/Sanju |  |  | SCRIPT 9
14 | Update CRM excel, zoho (All the followup can be added into note section) | Nick/Sanju/Nav

## Project Plan
Stages | Development Complete Date | Testing Complete Date | Handover Date for UAT
Sales Process | 3rd June 2020 | 7th June 2020 | 8th June 2020
Installation/Operation Process | 9th June 2020 | 11th June 2020 | 12th June 2020
Account Process | 14th June 2020 | 16th June 2020 | 17th June 2020

## Test Cases
Stage Name | TestCase #1 | Decription | Test Steps | Mandatory Fields | Input | Expected Output | Result
Sale Process | 1 | Creation of Leads | 1. Logging into CRM 2. Enter Credentials 3. Goto Lead Module 4. Create a new lead |  | Lead Name : | New leads to be created | Pass/Fail/Reopen
| 2 | Creation of Leads | 1. Logging into Do Solar website 2. Goto Contact us page 3. Enter the Details and Submit |  |  | New Leads to be created in the Zoho CRM

## Q & A
Stage Name | Description of Query | Date of Query | Resolution/Confirmation | Status
All